## Slide 1
WEEK 6 FINAL
Digital Transformation and
Operational Automation Plan
E-commerce order fulfillment operations
From manual tracking to a controlled, automated, KPI-driven operating model.
Practical transformation plan for operations coordination, workflow improvement, automation readiness, and performance control.
8
weeks
from assessment to monitoring
7
workflows
manual processes targeted
5
KPIs
core performance controls
01

## Slide 2
Current Manual Process Problem
Manual handoffs slow visibility, duplicate effort, and delay exception detection.
01
Where work slows down
Inventory checks, courier follow-ups, customer updates, and weekly reporting rely on manual coordination and spreadsheet updates.
02
What it affects
Order cycle time, delivery reliability, customer communication, inventory accuracy, and complaint handling.
03
Why automation matters
Teams need earlier alerts, consistent data fields, and a single source of truth for operational decisions.
Manual processes selected
Order status updates
Inventory checks
Pick & pack validation
Courier follow-ups
Customer notifications
Weekly reporting
Quality checks
Automation objective: remove repetitive updates while preserving human review for exceptions.
Week 6 | Digital Transformation and Operational Automation
02

## Slide 3
Current-State Workflow
Before automation, order visibility depends on manual updates at each handoff.
Order
received
Customer order enters system
Inventory
check
Manual stock lookup
Pick &
pack
Manual validation
Courier
assigned
Email/spreadsheet handoff
Tracking
Manual follow-up
Customer
issue
Complaint triggers review
Report
update
Manual weekly report
Manual lookup
Manual handoff
Manual follow-up
Late review
Main bottleneck
Exceptions are usually identified after a delay occurs, not while the order can still be recovered.
Improvement focus
Build early warning signals, standard data fields, and a controlled exception workflow.
Week 6 | Digital Transformation and Operational Automation
03

## Slide 4
Automation Opportunity Map
Each manual issue is matched to a practical digital solution and operational value.
Manual issue | Automation solution | Operational value
Manual order tracking | Order management workflow | Single source of truth
Manual inventory checks | Reorder alerts + stock dashboard | Lower stockout risk
Picking & packing errors | Barcode scanning + dispatch checklist | Better order accuracy
Courier follow-ups | SLA dashboard + exception alerts | Earlier delay detection
Manual customer updates | Auto email/SMS/WhatsApp templates | Consistent communication
Manual reporting | Power BI dashboard refresh | Faster KPI review
Start simple
Pilot the highest-value automations before scaling integrations.
Dashboard refresh
Delivery alerts
Customer templates
Then scale into deeper workflow and system integrations once the data fields are stable.
Week 6 | Digital Transformation and Operational Automation
04

## Slide 5
Future-State Automated Workflow
Automation adds early checks, exception alerts, and live operational visibility.
Order ID
created
Automatic status record
System
stock check
Availability validated
Barcode
pick
SKU scan confirms item
Auto
courier
Carrier assigned by rule
Live
tracking
Status sync + alerts
Customer
updates
Milestone messages
Daily KPI
dashboard
Refresh + review
At-risk exception alert
Human effort shifts
From repetitive status updates to exception handling, quality checks, and continuous improvement.
Control point added
Exceptions are identified while the order can still be recovered, improving delivery reliability.
Week 6 | Digital Transformation and Operational Automation
05

## Slide 6
Recommended Technology Stack
A practical stack that can start simple and scale after the pilot.
1
Order workflow
Order management system or structured tracker
Controls order status and handoffs
2
Inventory visibility
Inventory dashboard + reorder alerts
Flags low-stock and safety-stock risk
3
Warehouse control
Barcode scanner + dispatch checklist
Reduces picking and packing errors
4
Delivery monitoring
Courier SLA dashboard
Tracks delay risk by order and carrier
5
Customer communication
CRM/ticketing tool with templates
Sends consistent customer updates
6
Automation layer
Power Automate, Zapier, Make, or RPA
Handles reminders and repeated admin tasks
Tool selection rule
Choose the simplest system that provides reliable data fields, clear ownership, secure access, and measurable process improvement.
Week 6 | Digital Transformation and Operational Automation
06

## Slide 7
8-Week Implementation Roadmap
A phased rollout reduces disruption while testing automation in a controlled pilot.
W1
Assess
processes
Scope approved
W2
Select
tools
Requirements
W3
Prepare
data
SOP draft
W4
Build
automations
Prototype
W5
Pilot
workflow
Pilot results
W6
Train
teams
Training guide
W7
Rollout
Workflow live
W8
Monitor
Final KPI review
Prepare
Assess process, select tools, prepare data
Build & pilot
Prototype automation, pilot limited workflow
Deploy & monitor
Train, rollout, review KPIs and issues
Governance: weekly progress reviews, issue-log updates during the pilot, and KPI review after rollout.
Week 6 | Digital Transformation and Operational Automation
07

## Slide 8
Resources and Responsibilities
Clear ownership across operations, warehouse, customer service, and IT/data support.
Activity | Ops Manager | Ops Assistant | Warehouse Lead | Data Analyst | CS Lead
Scope and approvals | A | R | C | C | C
Dashboard build | C | C | I | R | C
Warehouse pilot | C | R | A | C | I
Customer templates | C | R | I | C | A
KPI review | A | R | C | R | C
RACI key
R
Responsible
A
Accountable
C
Consulted
I
Informed
Resource principle
Assign ownership before the pilot, not after issues arise. This reduces confusion and speeds up escalation.
Week 6 | Digital Transformation and Operational Automation
08

## Slide 9
Risk Management Strategy
Automation risks are manageable when rollout is phased and data quality is controlled.
High
Poor data quality
Clean mandatory fields before automation
High
Integration issues
Pilot with limited process scope first
High
Data security
Limit access and use approved platforms
Medium
Staff resistance
Train with simple SOPs and show time saved
Medium
Cost overrun
Prioritize low-cost automation first
Medium
Workflow disruption
Keep manual backup during pilot
Key control
Keep automation decisions traceable, protect customer data, and keep humans in the loop for exceptions.
Week 6 | Digital Transformation and Operational Automation
09

## Slide 10
Expected Benefits and KPIs
Success should be measured through a focused set of operational KPIs.
Current vs. target operating performance
Manual updates
100
35
Order visibility
45
85
Delay detection
35
80
Report cycle time
100
25
Inventory accuracy
82
94
Current
Target
1
Target state
Fewer repetitive tasks and stronger exception management.
2
Visibility
Daily KPI refresh supports faster action.
3
Quality
Barcode checks reduce order accuracy risk.
KPI review rhythm
Review dashboard weekly and escalate exceptions daily during rollout.
Week 6 | Digital Transformation and Operational Automation
10

## Slide 11
FINAL RECOMMENDATION
Start simple, prove value through a pilot, then scale the automation model.
Prioritize high-impact, low-cost automation first: dashboard refresh, delivery alerts, customer templates, and barcode validation before full system integration.
1
Document ownership rules
Every status change and escalation point has a named owner.
2
Pilot limited workflow
Use one product category or order segment to reduce rollout risk.
3
Track five KPIs
Delay rate, order accuracy, inventory accuracy, complaint rate, and report cycle time.
4
Review weekly
Use governance meetings to resolve issues and scale what works.
Outcome
Faster order processing, fewer manual errors, better delivery visibility, and stronger operational control.
11