## Dashboard
Week 3 Project Coordination and Scheduling
Project Coordination Plan for Improving E-Commerce Order Fulfillment and Delivery Performance
Project Snapshot
Project Name | E-Commerce Fulfillment and Delivery Improvement Project | Project Start | 2026-06-15 | Project End | 2026-08-07 | Duration | 8 weeks
Project Goal | Reduce fulfillment delays and improve visibility across warehouse, courier and customer service handoffs. | Project Sponsor | Operations Manager | Project Owner | Operations Assistant | Status | Planned
Scope | Order processing, warehouse handoff, courier coordination, delay alerts, customer communication and KPI reporting. | Primary Tools | Excel, Power BI, SOP checklist, weekly KPI tracker | Review Cadence | Weekly | Approach | Pilot then rollout
Project Control KPIs
Total Tasks | Completed | In Progress | Not Started | At Risk | High Priority | Milestones | Project Completion
26 | 0 | 1 | 25 | 0 | 20 | 5 | 1.731%
Main Deliverables |  |  |  | Expected Operational Impact
1 | Approved project charter and stakeholder register |  |  | Visibility | Weekly KPI reporting gives management clearer delivery performance visibility.
2 | Current-state process review and bottleneck assessment |  |  | Speed | Delay alerts help teams intervene before orders become overdue.
3 | KPI tracker, delay alert rules and exception dashboard setup |  |  | Quality | Warehouse handoff checklists reduce missing information and rework.
4 | Future-state SOP, courier SLA process and customer notification templates |  |  | Customer Experience | Proactive notifications reduce customer uncertainty during delays.
5 | Pilot implementation, rollout plan and final handover report |  |  | Accountability | Named owners and escalation paths improve follow-up and closure.

## Gantt Chart
Professional Excel Gantt Chart - 8 Week Project Timeline
Project Coordination Plan for Improving E-Commerce Fulfillment and Delivery Performance
Legend | Planned Work |  | Milestone |  | At Risk |  | Completed
ID | Phase | Task | Owner | Start | End | Duration | Status | Priority | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | Dependencies | Deliverable | Progress | Notes
[9 empty] | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03
1 | Project Initiation | Project kickoff and sponsor alignment | Operations Manager | 2026-06-15 | 2026-06-16 | 2 | In Progress | High | [9 empty] | Kickoff notes and agreed project direction | 45% | bar: 2026-06-15
2 | Project Initiation | Confirm scope, KPIs, baseline and target outcomes | Operations Assistant | 2026-06-16 | 2026-06-17 | 2 | Not Started | High | [8 empty] | 1 | Approved scope and KPI list | 0% | bar: 2026-06-15
3 | Project Initiation | Build stakeholder register and communication plan | Project Coordinator | 2026-06-17 | 2026-06-18 | 2 | Not Started | Medium | [8 empty] | 1 | Stakeholder and communication matrix | 0% | bar: 2026-06-15
4 | Project Initiation | Milestone: project charter approved | Operations Manager | 2026-06-19 | 2026-06-19 | 1 | Not Started | High | [8 empty] | 2,3 | Signed project charter | 0% | bar: 2026-06-15
5 | Current Process Review | Review current order fulfillment workflow | Operations Assistant | 2026-06-22 | 2026-06-24 | 3 | Not Started | High | [8 empty] | 4 | Current-state process notes | 0% | bar: 2026-06-22
6 | Current Process Review | Interview warehouse, courier and customer service stakeholders | Project Coordinator | 2026-06-22 | 2026-06-25 | 4 | Not Started | Medium | [8 empty] | 4 | Interview summary log | 0% | bar: 2026-06-22
7 | Current Process Review | Analyze delivery delay dashboard and operational findings | Data Analyst | 2026-06-24 | 2026-06-26 | 3 | Not Started | High | [8 empty] | 5 | Baseline performance analysis | 0% | bar: 2026-06-22
8 | Current Process Review | Identify bottlenecks, root causes and handoff risks | Operations Assistant | 2026-06-26 | 2026-06-29 | 4 | Not Started | High | [8 empty] | 5,6,7 | Bottleneck and root-cause summary | 0% | bar: 2026-06-22 to 2026-06-29
9 | Current Process Review | Milestone: current-state assessment approved | Operations Manager | 2026-06-30 | 2026-06-30 | 1 | Not Started | High | [8 empty] | 8 | Current-state assessment sign-off | 0% | bar: 2026-06-29
10 | Data and KPI Setup | Define KPI fields, calculation rules and reporting cadence | Data Analyst | 2026-07-01 | 2026-07-02 | 2 | Not Started | High | [8 empty] | 9 | KPI definition sheet | 0% | bar: 2026-06-29
11 | Data and KPI Setup | Prepare tracking template and Power BI/Excel source fields | Data Analyst | 2026-07-02 | 2026-07-06 | 5 | Not Started | High | [8 empty] | 10 | KPI tracking template | 0% | bar: 2026-06-29 to 2026-07-06
12 | Data and KPI Setup | Configure delay alert rules and exception tracker | Operations Assistant | 2026-07-06 | 2026-07-08 | 3 | Not Started | High | [8 empty] | 11 | Delay exception tracker | 0% | bar: 2026-07-06
13 | Data and KPI Setup | Validate data quality and reporting ownership | Project Coordinator | 2026-07-08 | 2026-07-10 | 3 | Not Started | Medium | [8 empty] | 11,12 | Data quality checklist | 0% | bar: 2026-07-06
14 | Data and KPI Setup | Milestone: KPI dashboard and tracker ready | Operations Manager | 2026-07-10 | 2026-07-10 | 1 | Not Started | High | [8 empty] | 13 | Dashboard sign-off | 0% | bar: 2026-07-06
15 | Workflow Improvement Design | Redesign warehouse-to-courier order handoff SOP | Operations Assistant | 2026-07-13 | 2026-07-15 | 3 | Not Started | High | [8 empty] | 14 | Updated SOP draft | 0% | bar: 2026-07-13
16 | Workflow Improvement Design | Define courier SLA review process and escalation path | Operations Manager | 2026-07-14 | 2026-07-16 | 3 | Not Started | High | [8 empty] | 14 | SLA review procedure | 0% | bar: 2026-07-13
17 | Workflow Improvement Design | Create customer notification templates for delayed orders | Customer Service Lead | 2026-07-16 | 2026-07-17 | 2 | Not Started | Medium | [8 empty] | 15 | Notification templates | 0% | bar: 2026-07-13
18 | Workflow Improvement Design | Prepare training materials, checklists and role guides | Project Coordinator | 2026-07-17 | 2026-07-20 | 4 | Not Started | Medium | [8 empty] | 15,16 | Training pack and checklist | 0% | bar: 2026-07-13 to 2026-07-20
19 | Workflow Improvement Design | Milestone: future-state design approved | Operations Manager | 2026-07-21 | 2026-07-21 | 1 | Not Started | High | [8 empty] | 15,16,17,18 | Future-state design sign-off | 0% | bar: 2026-07-20
20 | Pilot Implementation | Pilot improved process with selected sample orders | Warehouse Lead | 2026-07-22 | 2026-07-28 | 7 | Not Started | High | [8 empty] | 19 | Pilot run report | 0% | bar: 2026-07-20 to 2026-07-27
21 | Pilot Implementation | Monitor daily issues, delays and exception tracker updates | Operations Assistant | 2026-07-22 | 2026-07-30 | 9 | Not Started | High | [8 empty] | 20 | Daily issue log | 0% | bar: 2026-07-20 to 2026-07-27
22 | Pilot Implementation | Hold pilot review and corrective action meeting | Project Coordinator | 2026-07-30 | 2026-07-31 | 2 | Not Started | High | [8 empty] | 20,21 | Corrective action log | 0% | bar: 2026-07-27
23 | Pilot Implementation | Milestone: pilot sign-off | Operations Manager | 2026-07-31 | 2026-07-31 | 1 | Not Started | High | [8 empty] | 22 | Pilot approval | 0% | bar: 2026-07-27
24 | Rollout and Closure | Team training and go-live briefing | Project Coordinator | 2026-08-03 | 2026-08-04 | 2 | Not Started | Medium | [8 empty] | 23 | Training attendance and briefing notes | 0% | bar: 2026-08-03
25 | Rollout and Closure | Full rollout across fulfillment workflow | Operations Manager | 2026-08-05 | 2026-08-06 | 2 | Not Started | High | [8 empty] | 24 | Go-live confirmation | 0% | bar: 2026-08-03
26 | Rollout and Closure | Final performance review and handover report | Operations Assistant | 2026-08-07 | 2026-08-07 | 1 | Not Started | High | [8 empty] | 25 | Final project report and handover pack | 0% | bar: 2026-08-03

## Task Register
Task Register - E-Commerce Fulfillment and Delivery Improvement Project
ID | Phase | Task | Owner | Start Date | End Date | Duration | Status | Priority | Dependency | Deliverable | Progress %
1 | Project Initiation | Project kickoff and sponsor alignment | Operations Manager | 2026-06-15 | 2026-06-16 | 2 | In Progress | High |  | Kickoff notes and agreed project direction | 45%
2 | Project Initiation | Confirm scope, KPIs, baseline and target outcomes | Operations Assistant | 2026-06-16 | 2026-06-17 | 2 | Not Started | High | 1 | Approved scope and KPI list | 0%
3 | Project Initiation | Build stakeholder register and communication plan | Project Coordinator | 2026-06-17 | 2026-06-18 | 2 | Not Started | Medium | 1 | Stakeholder and communication matrix | 0%
4 | Project Initiation | Milestone: project charter approved | Operations Manager | 2026-06-19 | 2026-06-19 | 1 | Not Started | High | 2,3 | Signed project charter | 0%
5 | Current Process Review | Review current order fulfillment workflow | Operations Assistant | 2026-06-22 | 2026-06-24 | 3 | Not Started | High | 4 | Current-state process notes | 0%
6 | Current Process Review | Interview warehouse, courier and customer service stakeholders | Project Coordinator | 2026-06-22 | 2026-06-25 | 4 | Not Started | Medium | 4 | Interview summary log | 0%
7 | Current Process Review | Analyze delivery delay dashboard and operational findings | Data Analyst | 2026-06-24 | 2026-06-26 | 3 | Not Started | High | 5 | Baseline performance analysis | 0%
8 | Current Process Review | Identify bottlenecks, root causes and handoff risks | Operations Assistant | 2026-06-26 | 2026-06-29 | 4 | Not Started | High | 5,6,7 | Bottleneck and root-cause summary | 0%
9 | Current Process Review | Milestone: current-state assessment approved | Operations Manager | 2026-06-30 | 2026-06-30 | 1 | Not Started | High | 8 | Current-state assessment sign-off | 0%
10 | Data and KPI Setup | Define KPI fields, calculation rules and reporting cadence | Data Analyst | 2026-07-01 | 2026-07-02 | 2 | Not Started | High | 9 | KPI definition sheet | 0%
11 | Data and KPI Setup | Prepare tracking template and Power BI/Excel source fields | Data Analyst | 2026-07-02 | 2026-07-06 | 5 | Not Started | High | 10 | KPI tracking template | 0%
12 | Data and KPI Setup | Configure delay alert rules and exception tracker | Operations Assistant | 2026-07-06 | 2026-07-08 | 3 | Not Started | High | 11 | Delay exception tracker | 0%
13 | Data and KPI Setup | Validate data quality and reporting ownership | Project Coordinator | 2026-07-08 | 2026-07-10 | 3 | Not Started | Medium | 11,12 | Data quality checklist | 0%
14 | Data and KPI Setup | Milestone: KPI dashboard and tracker ready | Operations Manager | 2026-07-10 | 2026-07-10 | 1 | Not Started | High | 13 | Dashboard sign-off | 0%
15 | Workflow Improvement Design | Redesign warehouse-to-courier order handoff SOP | Operations Assistant | 2026-07-13 | 2026-07-15 | 3 | Not Started | High | 14 | Updated SOP draft | 0%
16 | Workflow Improvement Design | Define courier SLA review process and escalation path | Operations Manager | 2026-07-14 | 2026-07-16 | 3 | Not Started | High | 14 | SLA review procedure | 0%
17 | Workflow Improvement Design | Create customer notification templates for delayed orders | Customer Service Lead | 2026-07-16 | 2026-07-17 | 2 | Not Started | Medium | 15 | Notification templates | 0%
18 | Workflow Improvement Design | Prepare training materials, checklists and role guides | Project Coordinator | 2026-07-17 | 2026-07-20 | 4 | Not Started | Medium | 15,16 | Training pack and checklist | 0%
19 | Workflow Improvement Design | Milestone: future-state design approved | Operations Manager | 2026-07-21 | 2026-07-21 | 1 | Not Started | High | 15,16,17,18 | Future-state design sign-off | 0%
20 | Pilot Implementation | Pilot improved process with selected sample orders | Warehouse Lead | 2026-07-22 | 2026-07-28 | 7 | Not Started | High | 19 | Pilot run report | 0%
21 | Pilot Implementation | Monitor daily issues, delays and exception tracker updates | Operations Assistant | 2026-07-22 | 2026-07-30 | 9 | Not Started | High | 20 | Daily issue log | 0%
22 | Pilot Implementation | Hold pilot review and corrective action meeting | Project Coordinator | 2026-07-30 | 2026-07-31 | 2 | Not Started | High | 20,21 | Corrective action log | 0%
23 | Pilot Implementation | Milestone: pilot sign-off | Operations Manager | 2026-07-31 | 2026-07-31 | 1 | Not Started | High | 22 | Pilot approval | 0%
24 | Rollout and Closure | Team training and go-live briefing | Project Coordinator | 2026-08-03 | 2026-08-04 | 2 | Not Started | Medium | 23 | Training attendance and briefing notes | 0%
25 | Rollout and Closure | Full rollout across fulfillment workflow | Operations Manager | 2026-08-05 | 2026-08-06 | 2 | Not Started | High | 24 | Go-live confirmation | 0%
26 | Rollout and Closure | Final performance review and handover report | Operations Assistant | 2026-08-07 | 2026-08-07 | 1 | Not Started | High | 25 | Final project report and handover pack | 0%

## Milestones
Milestone and Deliverables Tracker
ID | Milestone | Target Date | Deliverable | Acceptance Criteria | Owner | Status
M1 | Project charter approved | 2026-06-19 | Signed project charter | Scope, project goal and responsible owners confirmed | Operations Manager | Not Started
M2 | Current-state assessment approved | 2026-06-30 | Process review and bottleneck assessment | Root causes and handoff risks clearly documented | Operations Manager | Not Started
M3 | KPI dashboard and tracker ready | 2026-07-10 | KPI tracker and delay exception rules | Reporting fields validated and owners assigned | Data Analyst | Not Started
M4 | Future-state design approved | 2026-07-21 | SOP, SLA review process and templates | Improved process map and role handoffs approved | Operations Manager | Not Started
M5 | Pilot sign-off | 2026-07-31 | Pilot report and corrective action log | Pilot completed with documented lessons learned | Operations Manager | Not Started
M6 | Project closure and handover | 2026-08-07 | Final performance review and handover report | Final report submitted with next-step owner | Operations Assistant | Not Started

## Resources RACI
Resource Allocation and RACI Matrix
Workstream | Operations Manager | Operations Assistant | Project Coordinator | Data Analyst | Warehouse Lead | Customer Service Lead | Courier Partner
Project initiation and governance | A | R | C | C | I | I | I
Current process review | A | R | R | C | C | C | C
KPI and dashboard setup | A | C | C | R | I | I | I
Warehouse handoff SOP redesign | A | R | C | C | R | C | C
Courier SLA and escalation process | A/R | C | C | I | C | I | R
Customer notification templates | A | C | C | I | I | R | C
Pilot monitoring and issue resolution | A | R | R | C | R | C | R
Training and rollout | A | R | R | I | R | R | C
Final handover and reporting | A | R | C | R | I | I | I
RACI Legend
R = Responsible | A = Accountable | C = Consulted | I = Informed | A/R = Accountable and Responsible

## Risk Register
Risk Assessment and Mitigation Register
ID | Risk Category | Risk Description | Probability | Impact | Risk Score | Owner | Mitigation Strategy | Contingency Plan | Status
R1 | Schedule | Project tasks take longer than expected due to stakeholder availability. | 3 | 4 | 12 | Project Coordinator | Use weekly progress check-ins and confirm meeting availability in advance. | Escalate overdue tasks and adjust non-critical activities. | Open
R2 | Data Quality | Order tracking fields are incomplete or inconsistent across teams. | 4 | 5 | 20 | Data Analyst | Standardize fields before dashboard setup and assign data ownership. | Use manual validation sample until automation is stable. | Open
R3 | Operational Adoption | Warehouse or customer service teams resist the updated process. | 3 | 4 | 12 | Operations Manager | Keep SOP simple and provide short training with role-specific checklists. | Run additional coaching and collect feedback during pilot. | Open
R4 | Courier Performance | Delivery partner performance does not improve after SLA review. | 3 | 5 | 15 | Operations Manager | Review SLA performance weekly and create an escalation path for late orders. | Compare alternative carriers for high-delay locations. | Open
R5 | Customer Experience | Customers remain dissatisfied if delay notifications are sent too late. | 3 | 4 | 12 | Customer Service Lead | Set notification triggers before expected delivery is missed. | Send proactive service recovery messages for high-risk orders. | Open
R6 | Technology | Power BI or tracker setup does not refresh as expected. | 2 | 4 | 8 | Data Analyst | Test refresh logic during setup and document ownership. | Use Excel tracker backup during pilot period. | Open
R7 | Scope Creep | Additional process changes are requested beyond the agreed project scope. | 3 | 3 | 9 | Operations Manager | Use change log and require approval for major scope additions. | Move non-critical ideas to the post-project improvement backlog. | Open

## Communication Plan
Stakeholder Communication Plan
Audience | Purpose | Format | Frequency | Owner | Timing | Output | Escalation Trigger
Project sponsor / Operations Manager | Confirm scope, decisions and roadblocks | Weekly meeting + summary email | Weekly | Project Coordinator | Every Monday | Decision log and action tracker | Blocked tasks or timeline slip over 2 days
Warehouse team | Review handoff process, issues and checklist usage | Stand-up meeting | Twice weekly during pilot | Warehouse Lead | Tue/Thu | Issue log and checklist updates | Repeated picking or handoff errors
Courier partner | Review SLA performance and delayed order exceptions | SLA review call | Weekly | Operations Manager | Wednesday | Courier action list | Late delivery rate exceeds target
Customer service team | Align delay notifications and customer response process | Briefing + template review | Weekly | Customer Service Lead | Thursday | Approved templates and feedback log | Customer complaints increase
Data analyst | Validate KPI fields, dashboard refresh and data quality | Working session | Weekly | Operations Assistant | Friday | Updated tracker and validation notes | Data gaps or dashboard refresh failure
All stakeholders | Share pilot outcome, rollout readiness and final handover | Final report and presentation | Project close | Operations Assistant | Week 8 | Final project report | Open risks remain unresolved

## Instructions
How to Use This Workbook
Step | Instruction | Sheet | Editable Fields | Notes | Quality Check
1 | Review the Dashboard first to understand the project scope and KPI cards. | Dashboard | Status snapshot if needed | KPI cards update from the Task Register when opened in Excel. | Check project dates and status.
2 | Use the Gantt Chart sheet as the main scheduling view. | Gantt Chart | Start, End, Status, Priority, Notes | The timeline bars are formula-based and update when dates change. | Check dates and dependencies.
3 | Update individual tasks and progress in the Task Register. | Task Register | Owner, Start Date, End Date, Status, Priority, Deliverable | Duration and progress are formula-driven. | Avoid deleting formulas.
4 | Track milestone completion and ownership. | Milestones | Status and owner | Use this for reporting key project checkpoints. | Confirm every milestone has a deliverable.
5 | Use the RACI matrix to explain resource allocation. | Resources RACI | RACI letters if ownership changes | R = Responsible, A = Accountable, C = Consulted, I = Informed. | Ensure each workstream has an accountable owner.
6 | Review and update risks during weekly project meetings. | Risk Register | Probability, impact, status, mitigation | Risk Score = Probability x Impact. | Escalate high scores.
7 | Use the Communication Plan to keep stakeholders aligned. | Communication Plan | Frequency, owner, escalation trigger | This supports the report submission requirement. | Check cadence and owners.